## Project
IROBOT BreakDown |  |  |  | Estimate Time:6/12 ------ 15/12 Actual Time: | Ideal Output Result: Bottons and switches could control the irobot and related info will be displayed.
Stage one: irobot communication via RS232
System Architecture | Estimated(day) | Actual(day) | Output | Actual Time Cost(Graph) |  | Status | Priority | Description
System Interface details | 0.4 |  | sytem interface details.pdf |  |  | Init | 1 | Split the project into small executable parts;Define their function and IO ports;Define the control flow
Input and Output | 0.1
Moduals Setup | 0.3
FSM Flow Chart | 0.2 |  | FSM Chart.pdf
Total | 1 | 0
FSM | Estimated | Actual | Output |  |  |  | Priority | Description
Input Output | 0.1 |  | FSM States Table.pdf |  |  | Init | 2 | Mainly define the state representation and coding
State change tables | 0.1
Coding | 0.6 |  | EmRobot_FSM.v
Testing | 0.2 |  | EmRobot_FSM_Test.v
Total | 1 | 0
CPU-idle | Estimated | Actual | Output |  |  |  | Priority | Desctiption
CPU functions defined | 0.5 |  | ====== |  |  | Hold | 7 | this module used to communicate with
CPU Interfaces defined | 0.5 |  | ======
Total | 1 | 0
Customer Control | Estimated | Actual | Output |  |  |  | Priority | Description
Botton Control interface | 0.1 |  | BottonSwtichesCtrol.pdf |  |  | Proc | 4 | The Swtiches and button to control the robot and display
Switch Interface | 0.2
Coding and Testing | 0.7 |  | EmRobot_CC.v
Total | 1 | 0
7-SEG | Estimated | Actual | Output | Estimated vs Actual( Graph) |  |  | Priority | Description
Display state define | 0.1 |  | 7SegDisplay.pdf |  |  | Proc | 5 | The 7-Seg used to show the Irobot OI command opcode(to detect the command is correctly conveyed)
submodule setup | 0.5 |  | EmRobot_SegControl.v
Coding | 0.2 |  | EmRobot_SegDisplay.v
Testing | 0.2 |  | SegDisplay_test.v
Total | 1 | 0
LCD1602 | Estimated | Actual | Output |  |  |  | Priority | Description
Display state define | 0.1 |  | LCD1602DisplayFunc.pdf |  |  | Proc | 6 | Used to show general info of the robot or the system(as a common monitor of the system)
Control module setup | 0.7 |  | EmRobot_LCD1602Control.v
Coding | 0.1 |  | EmRobot_LCD1602Display.v
Testing | 0.1 |  | LCD1602Display_test.v
Total | 1 | 0
CPU-controller | Estimated | Actual | Output |  |  |  | Priority | Description
function definition | 0.4 |  | CPUCtrolFuncFlow.pdf |  |  | Init | 3 | Mainly used to interface with FSM and RS232;decode and code the opcode and info for the irobot
interface with other module | 0.1
Control Flow Chart | 0.4
Coding | 0.4 |  | EmRobot_CPUCtrol.v
Testing | 0.7 |  | CPuCtrol_test.v
Total | 2 | 0
RS232(with FIFO) | Estimated | Actual | Output |  |  |  | Priority | Desctiption
Module iintegration | 0.5 |  | ====== |  |  | Hold | 7 | this module used to communicate with
Testing | 0.5 |  | ======
Total | 1 | 0
Total Expenses | Estimated | Actual |  | Delivered by Yuantao Zhang(Preston) | Version
| 8 | 0 |  | 2012-12-05 | 0.1
Note on C5: PrestonZhang: One Day Contains 5 working houres
Note on F5: PrestonZhang: Progress when process continuing
Note on H5: PrestonZhang: Init:Wait to begin Processing: Working on the project Stuck: Get stuck may need help and more time cost Hold:Waiting for relative project to be done Done:finished
Note on B19: PrestonZhang: Currently no CPU is needed
Note on F30: PrestonZhang: Progress when process continuing
Note on B52: PrestonZhang: Waiting for the module,if not,have to implement our own module